# CineScope Dissertation — Completion Plan

Student: Ruby Davies Deadline: 5 May 2026 Start date: 22 March 2026 Available time: 3–4 hours per day Total days: 44 days

## Overview: What Needs Doing

### Code Fixes (to align with report)

- Add a dedicated Film Diary page

- Fix navbar to use dynamic injection (report claims this)

- Fix timeline chart bug (all movies show same month)

- Add basic error handling to Compare and Streaming pages

- Add a simple login/registration system OR rewrite report to remove auth claims

### Report Fixes

- Fix section numbering (currently jumbled)

- Remove duplicate risk analysis table

- Fix Section 2.3 deliverables (still says "dental appointments")

- Change API references from TMDb to OMDb (or explain dual usage properly)

- Fix navbar claim (dynamic injection vs actual duplicated HTML)

- Add Analytics, Compare, and Streaming pages to Product Description

### Missing Report Sections

- Testing & Evaluation results (functional test cases + results table)

- Critical Review (evaluation of success, lessons learned, future improvements)

- Complete references list (currently only 7, need 30+)

### Appendices

- Wireframes / screenshots of the app

- Testing documentation (test cases table, results)

- Requirements traceability matrix

- Sprint plan / Gantt chart

- Won't-Have requirements list

- Code snippets / technical documentation

### Final Polish

- Proofread entire report

- Check all cross-references (e.g. "see Section 7")

- Ensure consistent formatting

- Generate table of contents

- Word count check

## PHASE 1: CODE FIXES (Days 1–8)

Fix the app so it matches what the report describes

### Day 1 — Sun 22 March

Focus: Film Diary page

- Create diary.html and diary.js

- Pull logged films from localStorage (recent key)

- Display in reverse chronological order with: poster, title, date logged, star rating, review

- Add empty state message ("No films logged yet — start exploring!")

- Add Diary link to the navbar on ALL pages

### Day 2 — Mon 23 March

Focus: Fix navbar + navigation consistency

- Create a navbar.js file that dynamically injects the navbar HTML into every page

- Remove hardcoded navbar HTML from all 6+ HTML files

- Replace with a <nav id="navbar"></nav> placeholder + script include

- This makes the report's Section 5.2.1 claim accurate

- Test all pages still work with the new dynamic navbar

### Day 3 — Tue 24 March

Focus: Authentication decision + implementation

- Option A (recommended — simpler): Rewrite the report to remove login/registration claims. Describe the Social page's auto-generated profile as "lightweight client-side identity" and explain that full auth was scoped out. This is honest and saves days of coding.

- Option B (harder): Build a simple localStorage-based register/login. Username + password stored in localStorage, session state tracked, pages conditionally render based on login status.

- Whichever you choose, make notes on what to update in the report.

### Day 4 — Wed 25 March

Focus: Bug fixes + error handling

- Fix the timeline chart in Analytics.js — store actual view dates when saving to recent (add a viewedDate field to each movie object in localStorage)

- Update saveRecentlyViewed() in omdb.js to include viewedDate: new Date().toISOString()

- Add try/catch error handling to fetch calls in Compare.js and Streaming.js

- Display user-friendly error messages instead of silent failures

- Test the streaming page with and without an API key

### Day 5 — Thu 26 March

Focus: Add Diary page to report's described features + small polish

- Make sure the Diary page matches what FR6 and UR5 describe

- Add a "remove from diary" option

- Make sure the watchlist page works consistently (either as inline on index.html or separate page — decide and stick with it)

- Test dark mode on the new Diary page

- Test responsive behaviour on all pages (mobile, tablet, desktop)

### Day 6 — Fri 27 March

Focus: Screenshots + visual evidence

- Take screenshots of EVERY page of your app (desktop + mobile for each)

- Search page, search results, movie detail modal, watchlist view

- Film diary page, analytics dashboard, compare page

- Social profile, ratings tab, reviews tab, friends tab

- Streaming page

- Dark mode versions of key pages

- Save all screenshots in a folder — you'll need these for appendices

### Day 7 — Sat 28 March

Focus: Testing your app systematically

- Go through each functional requirement (FR1–FR12) and test it manually

- For each one, write down: what you tested, input, expected result, actual result, pass/fail

- Test edge cases: empty search, no results, empty watchlist, no ratings yet

- Test on Chrome, Firefox, and Safari (or Edge) if possible

- Test responsive layout at 375px, 768px, and 1280px widths

- xRun your HTML through the W3C validator (validator.w3.org)

- Run Google Lighthouse on your main page — note the scores

- Save all results / screenshots

### Day 8 — Sun 29 March

Focus: Buffer day for code

- Finish anything from Days 1–7 that overran

- Do a final check that everything works end to end

- Make sure your GitHub repo is up to date with all changes

- After today, you should not need to touch the code again

## PHASE 2: FIX EXISTING REPORT (Days 9–14)

Get the current report sections accurate and properly structured

### Day 9 — Mon 30 March

Focus: Fix report structure and numbering

- Reorganise sections into this order:

  - Introduction (1.1 Problem Statement, 1.2 Solution Approach, 1.3 Project Scope)

  - Aims, Objectives and Deliverables

  - Requirements (Business, User, Functional, Quality)

  - Methodology (Project Management, Sprint Planning, Technology Choices, Risk Analysis)

  - Product Description

  - Research (Literature Review, Competitor Analysis, API Evaluation)

  - Testing and Evaluation (new)

  - Critical Review (new)

  - References

  - Appendices

- Remove the duplicate risk analysis table

- Remove the duplicate "Chosen Approach" section (fold any unique content into Methodology)

### Day 10 — Tue 31 March

Focus: Fix Section 2.3 Deliverables + Section 1

- Rewrite Section 2.3 to remove all "dental appointments" references

- List CineScope's actual deliverables: web application, wireframes, technical docs, testing docs, final report

- Review Section 1 — make sure the Introduction still reads well and accurately describes what CineScope is

- Check that the scope in Section 1.3 matches what you actually built (if you didn't build auth, don't claim it here)

### Day 11 — Wed 1 April

Focus: Fix Technology Choices section

- Update Section 4.3.4 (External Movie Database API) to accurately describe your ACTUAL setup:

  - OMDb API as the PRIMARY data source for search, movie details, ratings

  - TMDb API as SECONDARY, used specifically for trailer retrieval

  - Explain why both are used (OMDb for rich metadata, TMDb for video content)

- Update any other references throughout the report that say "TMDb" when they should say "OMDb"

- Make sure the API evaluation in Section 7.3 still makes sense with this correction

### Day 12 — Thu 2 April

Focus: Update Product Description (Section 5)

- Rewrite Section 5.1 to match your ACTUAL app structure:

  - Search/Home Page (index.html)

  - Film Detail Modal (not a separate page)

  - Film Diary Page

  - Watchlist (describe how it actually works)

  - Analytics Dashboard (NEW — not currently in report)

  - Compare Page (NEW — not currently in report)

  - Streaming Availability Page (NEW — not currently in report)

  - Social/Profile Page

- For Analytics, Compare, and Streaming: write 1–2 paragraphs each describing what they do and which requirements they support

### Day 13 — Fri 3 April

Focus: Update Product Description continued

- Rewrite Section 5.1.1 (Authentication) to match reality — either describe the localStorage profile system or the login system if you built one

- Rewrite Section 5.2.1 (Page Structure) to accurately describe dynamic navbar injection (if you've now built it) and multi-page architecture

- Update Section 5.2.3 (API Integration) to describe the OMDb + TMDb dual approach

- Update Section 5.2.4 (Client-Side Data Storage) to list ALL the localStorage keys you actually use

### Day 14 — Sat 4 April

Focus: Buffer day for report fixes

- Re-read the entire report from start to finish

- Flag any remaining inconsistencies between code and report

- Make sure every cross-reference ("see Section X") points to the right place

- Check that requirements tables are consistent and nothing contradicts

## PHASE 3: WRITE MISSING SECTIONS (Days 15–26)

This is the big one — Testing, Critical Review, References, Appendices

### Day 15 — Sun 5 April

Focus: Testing section — functional test cases table

- Create a table for functional requirement testing:

  - Columns: Test ID, Requirement, Test Description, Input, Expected Result, Actual Result, Pass/Fail

  - Write test cases for FR1 through FR12

  - Each requirement should have at least 1–2 test cases

  - Include edge cases (empty search, special characters, no internet)

### Day 16 — Mon 6 April

Focus: Testing section — quality requirement testing

- Document HTML validation results (W3C validator)

- Document CSS validation results

- Document Google Lighthouse scores (performance, accessibility, best practices, SEO) for desktop AND mobile

- Document responsive testing results at 3 viewport sizes

- Add screenshots of Lighthouse reports to your appendix folder

### Day 17 — Tue 7 April

Focus: Testing section — write the prose

- Write Section 7 (Testing and Evaluation) intro paragraph

- Write Section 7.1: Functional Testing — summarise results, note pass rates

- Write Section 7.2: Quality and Performance Testing — discuss Lighthouse scores, HTML validation, responsiveness

- Write Section 7.3: Usability Evaluation — describe any informal testing you did, what you observed, what you'd improve

- Reference the detailed test case tables in the appendix

### Day 18 — Wed 8 April

Focus: Critical Review — Evaluation of Project Success

- Write Section 8.1: Evaluation of Project Success

- What percentage of Must-Have requirements did you implement? (should be 100%)

- What percentage of Should-Have and Could-Have?

- Did you meet your project aim?

- Which objectives (from Section 2.2) did you achieve?

- What's the strongest part of the project?

### Day 19 — Thu 9 April

Focus: Critical Review — Lessons Learned

- Write Section 8.2: Lessons Learned

- Honest reflection — things like:

  - API choice (started with TMDb in mind, ended up using OMDb — why?)

  - Scope management (built extra features like Analytics/Compare that weren't in original requirements)

  - Time management (what took longer than expected?)

  - What would you do differently with vanilla JS vs a framework?

  - What did you learn about client-side storage limitations?

  - The authentication decision — why you scoped it in/out

### Day 20 — Fri 10 April

Focus: Critical Review — Future Improvements and Limitations

- Write Section 8.3: Future Improvements and Limitations

- API key exposure in client-side code

- No server-side backend (limits cross-device sync, real social features)

- localStorage capacity limits (~5MB)

- No real authentication/security

- Streaming page relies on external paid API

- Social features are simulated, not real multi-user

- What would a v2 look like? (backend, database, real auth, real social)

### Day 21 — Sat 11 April

Focus: References — gather all citations

- Go through the ENTIRE report and list every source you've cited

- For each one, write the full Harvard reference

- You should end up with 30–50 references

- Don't forget: OMDb API docs, TMDb API docs, Chart.js docs, MDN, W3C, Agile Alliance, Stack Overflow survey, etc.

- Check that every in-text citation has a matching reference entry

### Day 22 — Sun 12 April

Focus: References — finish + cross-check

- Complete the references list

- Alphabetise it

- Check formatting is consistent (Harvard style throughout)

- Cross-reference: go through every (Author, Year) in the report and verify it exists in the references

- Add any missing references

### Day 23 — Mon 13 April

Focus: Appendix A — Supervisor meetings + Ethics

- Write up your record of engagement with your supervisor

- Include dates and brief summaries of meetings

- Include any email exchanges (redact personal details if needed)

- Add your ethics checklist

### Day 24 — Tue 14 April

Focus: Appendix B — Project Plan / Gantt chart

- Create a sprint breakdown showing what you planned to do each sprint

- If you have a Gantt chart, include it

- If not, create a simple table: Sprint number, dates, planned features, actual outcome

- Show how your plan evolved (did you de-scope anything? add anything?)

### Day 25 — Wed 15 April

Focus: Appendix C — Wireframes + Screenshots

- Include your wireframes if you have them (even rough sketches are fine)

- Include the app screenshots you took on Day 6

- Label each screenshot clearly (e.g. "Figure D.1: Search Results Page — Desktop")

- Organise by page/feature

### Day 26 — Thu 16 April

Focus: Appendix D — Testing Documentation + Requirements Traceability

- Create the full test case tables (expand from what you wrote on Day 15)

- Create a requirements traceability matrix: Requirement ID → Test Case ID → Result

- Include Lighthouse report screenshots

- Include W3C validation screenshots

- Add Won't-Have requirements list

## PHASE 4: ASSEMBLY + POLISH (Days 27–38)

### Day 27 — Fri 17 April

Focus: Assemble the full document

- Put all sections together in the correct order

- Add page breaks between major sections

- Make sure heading styles are consistent (Heading 1, 2, 3)

- Generate a table of contents

### Day 28 — Sat 18 April

Focus: Formatting pass

- Check all tables are properly formatted and labelled ("Table 3.1: ...")

- Check all figures/screenshots have captions ("Figure 5.1: ...")

- Ensure consistent font, spacing, and margins throughout

- Number all pages

- Check header/footer consistency

### Day 29 — Sun 19 April

Focus: Read-through #1 — Content accuracy

- Read the entire report from start to finish

- Check: does every claim match your actual code?

- Check: do section cross-references point to the right places?

- Check: are requirement IDs consistent throughout?

- Make a list of issues to fix

### Day 30 — Mon 20 April

Focus: Fix issues from read-through #1

- Work through your issues list

- Fix any remaining inconsistencies

- Fill in any gaps you noticed

### Day 31 — Tue 21 April

Focus: Read-through #2 — Language and clarity

- Read again, this time focusing on writing quality

- Fix awkward sentences, typos, grammatical errors

- Check academic tone is consistent

- Remove any informal language

- Ensure you're not repeating yourself across sections

### Day 32 — Wed 22 April

Focus: Fix issues from read-through #2

- Apply all language fixes

- Tighten up wordy paragraphs

- Make sure the abstract still accurately summarises the whole project

### Day 33–34 — Thu 23 – Fri 24 April

Focus: Buffer days

- Catch up on anything that's behind schedule

- If you're on track, use these days for extra polish

- Consider: is there anything in the DentalConnect example that you admire but haven't done?

### Day 35 — Sat 25 April

Focus: Final references check

- One last pass on references

- Make sure nothing is missing

- Check all URLs are still accessible

- Verify Harvard formatting

### Day 36 — Sun 26 April

Focus: Update the abstract

- Rewrite the abstract to reflect the FINAL state of your project

- It should mention: what you built, what tech you used, what approach you followed, key results

- Keep it to one page

### Day 37 — Mon 27 April

Focus: Final read-through #3

- One complete read of the entire document

- This is your quality gate — if something feels off, fix it now

- Check word count is appropriate

### Day 38 — Tue 28 April

Focus: Generate final document

- Export/save the final version

- Generate table of contents one last time

- Check page numbers are correct

- Save a backup copy

## PHASE 5: SUBMISSION PREP (Days 39–44)

### Day 39–40 — Wed 29 – Thu 30 April

Focus: Exhibition preparation (if applicable)

- Prepare a brief demo of your app

- Make sure it runs smoothly

- Have your GitHub repo tidy and up to date with a good README

- Practice explaining your project in 2–3 minutes

### Day 41 — Fri 1 May

Focus: Final backup + pre-submission check

- Make sure your app is deployed/accessible (or at minimum runs locally)

- GitHub repo is clean and contains final code

- Report PDF/docx is the final version

- All appendices are included

### Day 42 — Sat 2 May

Focus: Rest day

- You've earned it. Step away from the screen.

### Day 43 — Sun 3 May

Focus: Pre-submission review

- Open the final document fresh

- Skim through — does it look professional?

- Check the submission requirements (file format, naming convention, where to submit)

- Prepare everything for upload

### Day 44 — Mon 5 May

Focus: SUBMIT

- Submit early in the day — don't leave it to the last hour

- Double-check you've submitted the right file

- Celebrate 🎉

## Daily Checklist Template

Use this each day:

- What's today's task?

- Did I complete it?

- Is there anything carrying over to tomorrow?

- Have I saved/backed up my work?

- Have I committed to GitHub (if code changes)?

## Emergency: If You Fall Behind

If you lose days to illness, other deadlines, or life — here's what to prioritise (in order):

- Fix the report–code mismatches (API, auth, features) — a marker WILL notice these

- Write the Critical Review — this is heavily weighted and currently missing

- Write the Testing section — even a basic one shows you evaluated your work

- Complete the references — incomplete references look unprofessional

- Appendices — important but less weighted than main body sections

- Code fixes — nice to have but the report matters more than perfect code

# CineScope — What's Left To Do

## REPORT FIXES (Small — do first)

- Delete the duplicate "8. Critical Review" line (the short one before the proper heading)

- Remove bold formatting from all references

- Remove "9." from the References heading — just "References"

- Fix Section 5.1.1 — either update for auth (if adding it) or rewrite as "User Profile and Identity Management" using the Day 3 plan

- Update the abstract to reflect the finished project (mention all features, OMDb API, testing results, Agile approach)

- Check Section 6.3.5 "Selected API" — it still says TMDb was selected as primary. Update to say OMDb was selected, with TMDb for trailers

## SCREENSHOTS (Medium — do in one sitting)

- Finish taking all screenshots from the Day 6 checklist

- Light mode screenshots (search, diary, analytics)

- Mobile width screenshots (search, hamburger, diary, modal)

- Save all in one folder called "screenshots"

## APPENDICES (Medium — build these out)

- Appendix A: Supervisor meetings log (dates + brief summaries)

- Appendix B: Ethics checklist (if you have one)

- Appendix C: Project Plan — already done (Gantt chart images)

- Appendix D: Wireframes + app screenshots (paste your screenshots here with captions)

- Appendix E: Technical documentation (file structure, setup instructions)

- Appendix F: Implemented requirements checklist (table showing which requirements were implemented)

- Appendix G: Testing documentation (paste the complete test results I gave you)

- Appendix H: Won't-Have requirements list

## TESTING (Small — quick jobs)

- Run through FR7–FR10 on your app to verify test results match

- Browser compatibility — open app in Safari, confirm each page works

- Fill in the browser compatibility table

## FORMATTING (Do near the end)

- Consistent heading styles throughout (Heading 1, 2, 3)

- All tables labelled (Table 3.1, Table 3.2, etc.)

- All figures/screenshots captioned (Figure D.1, etc.)

- Page numbers on every page

- Generate table of contents

- Check word count (aim for 10,000-12,000 words for main body)

- Consistent font and spacing throughout

## PROOFREADING (Do last)

- Read entire report start to finish — does it flow?

- Search for "dental" and "appointment" — should return 0

- Search for "TMDb" — should only appear for trailers and in Research

- Check all "see Section X" references point correctly

- Fix any typos or grammar issues

- Check "7. testing and evaulatation" typo in the heading — should be "7. Testing and Evaluation"

## OPTIONAL (If you have time)

- Add Firebase Auth (come back to me if you want to do this)

- Deploy to GitHub Pages or Vercel so markers can access it online

- Add a README to your GitHub repo

## SUBMISSION

- Push final code to GitHub

- Export report as final PDF/docx

- Check submission requirements (file format, naming, where to submit)

- Submit before deadline (5 May 2026)

- Celebrate 🎉

## PRIORITY ORDER (if short on time)

- Fix Section 5.1.1 (auth) — marker WILL notice this mismatch

- Paste references + remove bold

- Update abstract

- Build Appendix G (testing) and Appendix D (screenshots)

- Proofreading pass

- Everything else