## planning
Tasks | Oct |  |  |  |  | Nov |  |  |  | Dec
| 2nd | 9th | 16th | 23rd | 30th | 6th | 13th | 20th | 27th | 4th | 11th | 18th | 25th
Planning | bar: Oct 2nd to Oct 30th
Requirments | bar: Oct 30th to Nov 13th
Research | bar: Oct 9th to Nov 27th
Initial ui/wireframes | bar: Oct 30th to Nov 13th
Technical investigation | bar: Oct 16th to Oct 30th
Interim report | bar: Nov 6th to Dec 18th
Viva preparation | bar: Nov 13th to Dec 25th

## sprint development
Tasks | 2026-01-01 |  |  |  |  | 2026-02-01 |  |  |  | 2026-03-01 |  |  |  | 2026-04-01 |  |  |  |  | 2026-05-01
| 1st | 8th | 15th | 22nd | 29th | 5th | 12th | 19th | 26th | 5th | 12th | 19th | 26th | 2nd | 9th | 16th | 23rd | 30th | 1st | 3rd | 4th
Overall development phase
Sprint 1 : core setup & movie search | bar: 2026-01-01 1st to 2026-01-01 15th
Sprint 2 : movie details page | bar: 2026-01-01 15th to 2026-01-01 29th
Sprint 3 : rating and reviews | bar: 2026-01-01 22nd to 2026-02-01 12th
Sprint 4: watchlist and recently watched | bar: 2026-02-01 12th to 2026-03-01 12th
Sprint 5: optional features / stretch goals | bar: 2026-02-01 19th to 2026-03-01 26th
sprint 7 : UI polishing & UX | bar: 2026-03-01 26th to 2026-04-01 16th
Sprint 8 : testing and bug fixes | bar: 2026-04-01 2nd to 2026-04-01 23rd
Submission Report | bar: 2026-03-01 19th to 2026-05-01 4th
First draft | bar: 2026-03-01 19th to 2026-04-01 9th
second draft | bar: 2026-04-01 9th to 2026-04-01 23rd
Final draft | bar: 2026-04-01 30th to 2026-05-01 4th